## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 | 2021-04-12 | 42 | 2021-05-23 | 306
2 | 2021-05-24 | 0 | 2021-05-23 | 0
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
1 | 2021-04-12 | 14 | 2021-04-25 | 92 | Planned |  | Main functionality (Add and Get Sub List functions) | 1
2 | 2021-04-26 | 14 | 2021-05-09 | 102 | Planned |  | Main functionality (Update and Delete functions), Security | 1
3 | 2021-05-10 | 14 | 2021-05-23 | 112 | Planned |  | Quality of life features, Aesthetics and Security | 1
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 0
Formulas:
Start = IF(OR(B16="",[Incr.]=""),"",B16)
Start = IF([Incr.]="","",[Start, row above]+[Days, row above])
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Comments
1 | As a customer I want to be able to add an entry for my subscriptions so that I can be reminded when they are close to expiring. | Done | 34 | 1 | High | - “Subscriptions” is a term we are using to loosely define service subscriptions, licenses and free trials - A reminder refers to an email notification from the application with details of the subscription due to expire. - “Close to expiring” could mean 7 days or 1 day prior to the expiration date | Total Size
2 | As a designer I want to be able to keep track of all costs of my application licenses in one place so that I can budget and price my work appropriately. | Done | 5 | 1 | High |  | 306
3 | As a gamer I want to be able to keep track of my MMO subscriptions so that I know when my subscriptions are renewing or expiring. | Done | 13 | 1 | High
4 | As a full-time student I want to be able to write additional comments on the added subscription so that I can quickly view anything I need to remember regarding the subscription with a quick glance. | Done | 2 | 1 | Low
5 | As a consumer I want to view the total cost of my subscriptions every month so I am able to budget with my other expenses. | Ongoing | 3 | 2021-01-02 | Medium
6 | As a user I want to have access to the subscription provider’s home page to quickly make changes to my subscription in case I'm still unsure which one works for me. | Planned | 2 | 3 | Medium | - “Changes” can be defined as switching subscription plans.
7 | As a homeowner and family person I want to be able to filter my subscriptions by category so that I can separate household utility services and household entertainment services. | Ongoing | 8 | 2 | High
8 | As a low income earner I want to sort my current subscriptions by expiration date so that I can take preemptive action for any subscriptions about to expire. | Ongoing | 13 | 2 | High | - Another user story can be generated by replacing expiration with renewal - For example, this will prompt me to search for a new subscription service of the same category (assuming dissatisfaction with current provider) or ensure financial readiness for the renewal transaction.
9 | As an avid consumer I want to be able to delete a subscription from my profile when it has ended to avoid having inactive subscriptions crowding my account. | Ongoing | 21 | 2 | High
10 | As a customer I want to create a new account so that I know which subscriptions are tied to my account. | Done | 8 | 1 | High
11 | As a user I want to use my email as a form of two-factor authentication (2FA) when creating or logging into my account so that my account can remain protected | Planned | 55 | 3 | Low
12 | As a contractor I want to be able to login to a subscription tracker application so I can see all the subscriptions tied to my account. | Done | 13 | 1 | High
13 | As a parent I want to look at the subscriptions on my own account and my child’s account so that I can moderate my child’s subscriptions. | Planned | 55 | 3 | Low
14 | As a budgeter I want to be able to input number literals into the subscription's details so I know how much each of my clients' subscriptions cost. | Done | 1 | 1 | High | - Number literals were chosen because they were thought to be simpler to implement than having some form of currency conversion. - With the above comment in mind, this means that if a user lives in NZ and moves elsewhere, the subscription cost doesn't change. It is up to them to change the cost.
15 | As a developer I want the system to automatically issue a reminder once the date has changed, and it is within the specified amount of days before a subscription ends. | Ongoing | 12 | 2 | High
16 | As a developer I want the users to have the ability to add a company that they are subscribed to when they are not able to search for it. | Done | 1 | 1 | High
17 | As a user I want to update my subscription details so I can account for any unforeseen changes. | Ongoing | 12 | 2 | High
18 | As a contractor I want to be able to securely log in so that I can protect my clients data | Planned | 15 | 3 | High
19 | As a developer I want the subscription data to be stored in the database so that data can be stored persistently | Done | 21 | 2 | High
20 | As a user I want to go to a website so that I can look at my subscriptions from a web browser | Done | 12 | 3 | High
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 306 |  | Sprint count | 3
Count trend from last |  |  | 3 | sprints | Trend sprint count | 3
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  |  |  | Sprints in Trend | 3 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 30 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 |  |  | 55 | [12 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  | 55 |  | Trend count | 4 | [9 empty] | (i.e. if the amount of story points
Average last 8 |  |  | 55 | [12 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 |  |  | 55 | [12 empty] | of the bars indicate the estimated size of the project at the
Trend |  |  | 55 | [12 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 7
Original estimate - Avg |  |  | 11
Original estimate - Max |  |  | 17 |  | Standard Dev. | 48.0833
3 |  |  | 6
Realized average |  |  | 6 |  | LastPlanned | 196
Average last 8 |  |  | 6 |  | LastRealized | 0
Avg. worst 3 in last 8 |  |  | 6
Trend |  |  | 3
Realized + St. Dev |  |  | 4
Realized - St. Dev |  |  | 31
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 | 306 | 92 | 89 | 306 | 306 | 306 | 0 | 0 | 306 | 294.6667 | 294.6667 | 0 | 55 | 55 | 55
2 | 217 | 102 | 21 | 306 | 217 | 217 | 0 | 0 | 217 | 239.6667 | 239.6667 | 0 | 55 | 55 | 55
3 | 196 | 114 |  | 306 | 196 | 196 | 0 | 0 | 196 | 184.6667 | 184.6667 | 0 | 55 | 55 | 55
4 | [9 empty] | 129.6667 | 129.6667 | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
[10 empty] | #VALUE! | #VALUE! | 0 | 55 | 55 | 55
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 33 | 33 | 30 | 23 | 21
Task rows | 4 | Done days | 4 |  | 33 | 26.4 | 19.8 | 13.2 | 6.6
Warning! These are necessary |  | Trend |  |  | 33.2 | 28.9 | 24.6 | 20.3 | 16 | 11.7 | 7.4 | 3.1
template rows |  | Trend Days | 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 33.2 1: 1; 28.9 2: 2; 24.6 3: 3; 20.3 4: 4; 16 5: 5
Example task | 1 | Danny Dev | Done | 5 | 33.2 1: 5; 28.9 2: 2; 24.6 3: 0 | See https://isgb.otago.ac.nz/info310/syela651/SubscriptionTracker/issues for more details
Example task 2 | 1 | Tina Tester | Ongoing | 7 | 33.2 1: 7; 28.9 2: 7; 24.6 3: 2; 20.3 4: 2
Example task 3 | 2 | Danny Dev | Ongoing | 12 | 33.2 1: 12; 28.9 2: 12; 24.6 3: 12; 20.3 4: 10
<Delete these example lines> | 2 |  | Planned | 9 | 33.2 1: 9; 28.9 2: 9; 24.6 3: 9; 20.3 4: 9
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
See https://isgb.otago.ac.nz/info310/syela651/SubscriptionTracker/issues for more details
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Task Slips
Story ID: | 1 | Story: | This is a sample story
Task: | Example task |  |  |  | See https://isgb.otago.ac.nz/info310/syela651/SubscriptionTracker/issues for more details
Responsible Person: Danny Dev
Initial Estimate | 5 | Work Done |  | Work Left
Story ID: | 1 | Story: | This is a sample story
Task: | Example task 2
Responsible Person: Tina Tester
Initial Estimate | 7 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | Example task 3
Responsible Person: Danny Dev
Initial Estimate | 12 | Work Done |  | Work Left
Story ID: | 2 | Story: | This is another sample story
Task: | <Delete these example lines>
Responsible Person:
Initial Estimate | 9 | Work Done |  | Work Left